## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | 32
PROJECT NAME | Fixing Expressions By Stitching The Best One
PROJECT MENTOR (sponsor) | Jaya Bharadwaj
TEAM MEMBERS | Morampudi Srisai Krishna
Vemula Saketh Reddy
Ishita Bansal
Yashas B
Saideekshith Vaddineni

## Status
PROJECT NUMBER | 32
PROJECT NAME | Fixing Expressions By Stitching The Best One
PROJECT MENTOR (sponsor) | Jaya Bharadwaj From Joly AI
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error%
See Instructions sheet for usage
Week 1 (February 1 - February 8)
Fix meeting with client | Coordination | Mahika Jain (TA) | 0.5 | 0.5 | Done | Got a basic idea and goal of the project | 0 | 0
GIT Repository setup | Preparation | Ishita | 1 | 0.5 | Done |  | 0.5 | 100
Client Meeting - 1 | Coordination | Mahika Jain (TA) | 1 | 0.75 | Done | Make sure scoping questions are included | 0.25 | 33.3333
MoM Document of the Week | Preparation | Sai Krishna | 1 | 1 | Done | Researching on the points client has mentioned | 0 | 0
Project synopsis writeup | Documentation | Saketh Reddy, Sai Krishna | 1.5 | 2 | Done | Created a basic documentation about the project | -0.5 | 25
Status tracker | Documentation | Sai Krishna | 0.5 | 1 | Delayed | Delayed by 1 day because of assignment deadline (updated on 9th february) | -0.5 | 50
Week 2 (February 9 - February 18)
Research existing technology | Preparation | Whole Team | 7 (each) |  | Ongoing | Researching on PyTorch , Reverse emgineering on photoshaop app, etc
Project Plan | Documentation | Saketh Reddy | 1 | 0.5 | Delayed | Delayed by 1 day because of some confusion with the deadline | 0.5 | 100
MoM Document | Documentation | Yashas | 1 | 2 | Done | Created on the next day of the meeting | -1 | 50
Client Meeting - 2 | Coordination | Whole Team | 0.5 | 2 | Done | Got an green signal for the project that is got a detailed idea about the project. Meeting has been done on 14th | -1.5 | 75
SRS Document | Documentation | Saideekshith, Yashas | 3 | 4.5 | Done | SRS document made and uploaded. | -1.5 | 33.3333
Status Tracker | Documentation | Sai Krishna | 0.25 | 0.15 | Done | From now on the status tracker will be updated every Sunday. | 0.1 | 66.6667
Analyizing the Dataset | Preparation | Sai Krishna | 3 | 4 | Ongoing | Client given the team the dataset and told us to observe each and every photo. This is one fo the trasks given by the client for this week | -1 | 25
Week 3 (February 19 - February 25)
Client Meeting - 3 | Coordination | Whole Team | 0.5 | 1.5 | Done | Discussed about technical models to be used. Discussed few advanced models which needed to be used in the project. | -1 | 66.6667
Study the methods of face detection | Preparation | Ishita | 1 | 1 | Ongoing | Study the existing methods of face and features detection in computer vision | 0 | 0
MoM Document | Documentation | Ishita | 1 | 1 | Done | Created on the same day of the meeting | 0 | 0
Blending the edges after patching | Development | Yashas | 3 | 1.5 | Ongoing | Explored some new libraries from Python and will continue to do so with help from GPT-4 | 1.5 | 100
Reverse Engineering on Photo Editing Software | Preparation | Yashas | 2.5 | 3 | Done | Tried to find source code for GIMP (an open source photo editing software). Tried to make API calls to the application with python. | -0.5 | 16.6667
Exploring various scoring methods available | Preparation | Saketh Reddy | 2.5 | 3 | Done | Found few papers based on Neural Network, Geometry of Facial landmarks. | -0.5 | 16.6667
Analyzing different emotions | Preparation | Saketh Reddy | 3 | 4 | Done | Found feature extraction methods based on distances, cosines of Facial landmarks | -1 | 25
PatchSwap | Development | Saketh Reddy | 2 | 3 | Done | Read paper PatchSwap provided by the client and implemented it in code | -1 | 33.3333
Key Points Detection using basic models | Development | Saideekshith, Saketh Reddy | 2 | 1 | Done | Used openCV for Face detection and dlib for 68 landmark detection. Came to conclusion that these models are not at all accurate for project. | 1 | 100
Setting up fastdeploy and pytorch | Preparation | Saideekshith, Sai Krishna | 3 | 3 | Done | Setting up fastdeploy module for performing face detection | 0 | 0
Researching On GANs | Preparation | Sai Krishna | 5 | 2 | Ongoing | Exploring open-sources used for GANs based development (Mostly used after release-1). | 3 | 150
Status Tracker | Documentation | Sai Krishna | 0.5 | 1 | Done | Tried to find source code for GIMP (an open source photo editing software). Tried to make API calls to the application with python. | -0.5 | 50
Week 4 (February 26 - March 3)
Accurate Face Detection | Development | Saketh Reddy | 2 | 2.5 | Done | Used FastDeploy's RetinaFace for accurate face detection for low quality group photos | -0.5 | 20
Face Key Points Detection | Development | Saketh Reddy, Saideekshith | 2 | 2 | Done | 3D face mesh using Google's pre-trained MediaPipe API's | 0 | 0
Scores On The Plotted Key Points | Development | Saketh Reddy | 2.5 | 1 | Done | Used MediaPipe API for calculating scores of different facial features so that it can be used for further scoring methods | 1.5 | 150
Status Tracker | Documentation | Sai Krishna | 0.5 | 0.5 | Done | This week's whole team progress is very low because of our academics midsem examinations. Same reason for not having a client meeting and MoM of it for this week. | 0 | 0
Week 5 (March 4 - March 10)
Client Meeting - 4 | Coordination | Whole Team | 1.5 | 4 | Done |  | -2.5 | 62.5
Researching On Tools of Face Morphing | Preparation | Saideekshith | 5 | 5 | Ongoing |  | 0 | 0
Face Morphing using pretrained models | Development | Saketh Reddy | 10 | 13 | Done | Used a pre trained model for face morphing when we don't have perfect image for patching. | -3 | 23.0769
Mini Dataset for Use cases | Preparation | Saketh Reddy | 1 | 1 | Done | Prepared a mini dataset where we can identify and apply our use cases. | 0 | 0
Patching and Blending of images | Development | Sai Krishna, Yashas | 5 | 6 | Ongoing | We have made a testing dataset. We have tried to use GIMP to understand what the process is. We have collected information about the modules used. | -1 | 16.6667
MoM Document | Documentation | Yashas | 2 | 3 | Done | Created on the next day of the meeting | -1 | 33.3333
Design Document | Design | Sai Krishna | 7 | 8 | Done |  | -1 | 12.5
Status Tracker | Documentation | Sai Krishna | 0.5 | 0.5 | Done | This week, the whole team understood the final implementations required to be presented for release-1 and started working on it. | 0 | 0
Week 6 (March 11 - March 17)
Team Meeting - 1 | Coordination | Sai Krishna, Yashas, Saketh Reddy, Saideekshith | 1 | 1 | Done |  | 0 | 0
Patching and Blending of images | Development | Sai Krishna, Yashas | 5 | 14 | Ongoing | Tried to generate code with help of GenAI, this did not work. So tried to make program with the help from open source gitrepos and write code by ourself. | -9 | 64.2857
Clustering for Faces | Development | Saideekshith | 5 | 7.5 | Done | UMAP clustering for creating Mini-clustering of each face clusters | -2.5 | 33.3333
Integrating clustering with Face Morphing | Development | Saketh Reddy | 7 | 8 | Ongoing | Made a modular code by integrating all the subparts | -1 | 12.5
Documents Modification | Documentation | Sai Krishna, Saideekshith | 2 | 4 | Done |  | -2 | 50
Web Interface | Development | Sai Krishna | 3 | 3 | Done |  | 0 | 0
Status Tracker | Documentation | Sai Krishna | 1 | 1 | Done | This whole week, the team was preparing for the release-1 | 0 | 0
Week 7 (March 18 - March 24)
Team Meeting - 2 | Coordination | Whole Team | 2 | 2 | Done | Discussed about the R1 presentation methods | 0 | 0
R1 Presentation | Documentation | Whole Team | 5 | 5 | Done | Created a powerpoint ppt and presented it on Tuesday for the R1 grading | 0 | 0
OOP Implementation | Development | Yashas | 4 | 5 | Done | Basically all of our codes were not implemented in oop so changing/modifying the codes to oop by naming different classes and objects in it | -1 | 20
Status tracker | Documentation | Sai Krishna | 0.5 | 0.5 | Done | Took a break after R1 and will start developing the interface and GANs methods from next week | 0 | 0
Testing patch extracter and morpher | Testing | Yashas, Saketh Reddy | 1 | 1 | Ongoing | Tested the morphing tool and patch extracter upon different photos and settings | 0 | 0
Week 8 (March 25 - March 31)
Client Meeting - 5 | Coordination | Whole Team | 2.5 | 2.5 | Done | Discussed The Plans and Work Division For Release 2 Progress | 0 | 0
MoM Documentation | Documentation | Ishitha | 1 | 1 | Done |  | 0 | 0
Web Interface | Development | Sai Krishna | 1 | 0.5 | Ongoing | Basic frontend part is expected and the requirements are known in client meeting. So started working on it | 0.5 | 100
Researching On GANs | Preparation | Sai Krishna,Saketh Reedy, Ishitha | 5 | 4 | Ongoing | Searching methods for smile,eyes,….etc correction in faces | 1 | 25
Researching On Better Blending Techinques | Preparation | Saideekshith, Yashas | 2 | 3 | Ongoing | Searching for patching and blending pieces smoothly | -1 | 33.3333
Status Tracker | Documentation | Sai Krishna | 0.5 | 0.5 | Done | Came to know anout the R2 requorements and steps to implement them in this week, so there is no much progress like 8 hrs per week | 0 | 0
Week 9 (April 1 - April 7)
Web Interface | Development | Sai Krishna | 1 | 1 | Ongoing | Started Working on some front-end part | 0 | 0
Learning About StyleGANs2 Techniques | Preparation | Sai Krishna | 5 | 7 | Ongoing | Choose this type of GANs because it might have simple modules for correcting face expressions | -2 | 28.5714
Learning About Gaussian Blur | Preparation | Saketh Reddy , Saideekshith | 5 | 6 | Ongoing | Exploring it for blending techniques | -1 | 16.6667
Integrating the Existing Modules | Development | Yashas | 10 | 7 | Ongoing | The previous modulues were not combined. So it first so that we can work on others | 3 | 42.8571
Learning About Photoshop methods | Preparation | Saketh Reddy , Ishitha | 3 | 5 | Ongoing | Knowning how the photoshop tools work out so that we can implement in a similar way | -2 | 40
Status tracker | Documentation | Sai Krishna | 0.5 | 0.5 | Done | The times arre not matched because of dass and other courses assignments and quiz schedule | 0 | 0
Week 10 (April 8 - April 14)
Implementing and Testing patching with blending | Testing | Saketh Reddy | 36 | 36 | Done | Used affine transformation for pasting the patch and used Poisson blending for smoothening the edges and adjusting the colors. | 0 | 0
Face Pose Estimation for filtering target images | Development | Saketh Reddy | 4 | 4 | Done | Devised a pipeline and implemented the face pose estimation for automating the selection of the target image from the clusters | 0 | 0
Client Meeting - 6 | Coordination | Saketh Reddy, Saideekshith, Sai Krishna, Yashas | 3 | 5 | Done | Discussed About the upcoming week part | -2 | 40
MoM Documentation | Documentation | Sai Krishna | 1 | 1 | Done | Mentioned few points discussed in the client meeting | 0 | 0
Web Interface | Interfaces | Sai Krishna | 17 | 17 | Ongoing | A basic interface is developed for representation purpose | 0 | 0
Integrating Individual Modules | Development | Yashas | 3 | 3 | Done | Integrated the EyePatch code with the landmarks detector code | 0 | 0
Understood the architecture of GANs | Preparation | Yashas, Saideekshith | 3 | 3 | Done | Understood how GANs works with the help of some online resources. | 0 | 0
Various GANs Exploration | Preparation | Yashas, Saideekshith | 10 | 12 | Ongoing | Looked into different open-source GANs models and tried to check their implementation. Explored the synergy between these GANs models and our existing software | -2 | 16.6667
Status Tracker | Documentation | Sai Krishna | 0.5 | 0.5 | Done | Almost Completed the madatory functionalities mentioned in SRS(v2) document | 0 | 0
Week 11 (April 15 - April 21)
Status tracker | Documentation | Sai Krishna | 0.5 | 0.5 | Done | Completed tracking everything in this project. Every activity name mentioned above has been completed | 0 | 0
Revisiting Documentation | Delivery | Whole Team | 5 | 5 | Done | Completely changed each and every doc according to the current system and vice-versa | 0 | 0
Testing Patch and Blending with automation | Testing | Saketh Reddy | 12 | 12 | Done | Tested the newly devised method for automatically selecting target images. Tested the entire integrated code for all the datasets. | 0 | 0
GANs implementation and testing | Development | Yashas and Saideekshith | 24 | 48 | Done | Implemented GANs and changed some functionalities to suit our requirements | -24 | 50
Reiterated the code for meeting modularity and README | Development | Saketh Reddy | 3 | 3 | Done | Ensured the codes are in OOPs and doc strings for each classes. Wrote the README explaining the codes. | 0 | 0
Web Interface | Interfaces | Sai Krishna | 3 | 3 | Done | Completed a basic interface for better R2 presentation (This is a bonus part) | 0 | 0
GIT Repository setup & Team Meeting | Delivery | Whole Team | 2.5 | 2.5 | Done | Pushed everything into the github and discuused about the presentation features | 0 | 0
Note on C5: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on H5: SE: This field is updated automatically
Note on I5: SE: This field is updated automatically